## Overall Summary
Workstream Overview: | [11 empty] | Date :25/03/2026
| CAB | Yet to Create
| Sprint | 3 | [6 empty] | QA Exexution Progress |  |  |  | 100%
| Sprint Cycle | 2nd Mar - 13th Mar | [6 empty] | Story | TS Coverage | Pass | Fail | Blocked | Deferred | Pending
| Say/Do Ratio | 100% | [6 empty] | 6 | 49 | 49 | 0 | 0 | 0 | 0
| Overall Status | Green
Progress Summary this Cycle
- Worked on fixing existing master script failures - 6 New test case added for Renewall and Amendment and OnDemand order creation. - Scripting Completed for Renewal, amendment & OnDemand order scenarios, Paymonthly project changes, Adhoc order creation scenarios from Roadmap/Project team, - Updated scripts based on the new Order page UI changes and bulk data Order creation, fulfillment and shipments details process. - 6 application defects logged through automation ( QETA-27727 , QETA-27735, QETA-27807, QETA-27904, QETA-27807, QETA-27897 )
Issues & Risks
-
| Defects Trend | P0 | P1 | P2 | P3 | P4 |  |  | Progress This Cycle |  | stories ready for QA | stories QA In-Progress | stories QA Completed | stories ready for UAT | UAT Completed
| Open | #REF! | #REF! | #REF! | #REF! | 0 | #REF! |  | Stories |  | 0 | 0 | 6 | 5 | 1
| Closed | 2 | 2 | 3 |  | 0 | 7 |  | Tasks |  | 0 | 0 | 0 | 0 | 0
| Reopen | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 6 | 5 | 1
[7 empty] | #REF! |  | Total Stories Planned |  | 6
[9 empty] | QA Qualified |  | 6
[9 empty] | Spill-Overs |  | 0
| Automation Coverage | [5 empty] | #DIV/0!
| Automation Candidates | Cannot Be Automated |  | Automated Tests |  | Pending TCs for Automation |  | Partially Automated - Feature not developed
| 0 | 13 |  | 0 |  | 14 |  | 22

## TestCase Coverage
Coverage | 100% | [10 empty] | #DIV/0!
Story | TS Coverage | Pass | Fail | Blocked | Deferred | In Progress | Pending | Automation Candidates | Cannot Be Automated | Automated Tests | Pending TCs for Automation | Partially Automated - Feature not developed
PRDOPS-490 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
PRDOPS-415 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0
PRDOPS-413 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
PRDOPS-477 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
PRDOPS-470 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
PRDOPS-23 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
6 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 14 | 22
Story | Module | Test Case ID | Test Case | Test Case Description | Expected Result | Status | Tested by | Identified for Automation | Automated
PRDOPS-490 | NS | PRDOPS-490-TC-001 | Verify that NS-SFDC Sync Status is updated to "Failed" in the NetSuite Fulfillment Status Record. | Verify Integration Response Record Creation in NetSuite | 1.NS-SFDC Sync Status = "Failed" 2.Failure reason is logged correctly. 3.No incorrect status like Success/Completed. | Pass | Madhu Peketi | No | Cannot Automate
| NS | PRDOPS-490-TC-002 | Verify NetSuite sends failure notification email twice daily. - Schedule: Daily 11.45 PM PST and 11.45 AM PST | Email Trigger – Twice Daily | 1.Email sent twice daily. 2.Trigger occurs only if failed records exist. 3.No duplicate emails within same schedule cycle. | Pass | Madhu Peketi | No | Cannot Automate
| NS | PRDOPS-490-TC-003 | Validate Subject, Recipient and Body of email. | Email Content Validation | Subject must be exactly: Report: Order failed to shipped in SFDC To: prodopsapps@rubrik.com Email Body must contain: Hi Team, Please find attached the list of order failed to get shipped in SFDC. Review and try to fix this asap. Thanks! | Pass | Madhu Peketi | No | Cannot Automate
| NS | PRDOPS-490-TC-004 | Verify CSV file attachment and its contents. | CSV Attachment Validation | 1.CSV file attached. 2.File opens without corruption. 3.Contains correct columns (Example): Order Number Fulfillment ID Failure Reason Sync Status Timestamp 4.Data matches NetSuite failed records. | Pass | Madhu Peketi | No | Cannot Automate
| NS | PRDOPS-490-TC-005 | Verify all failed records are included in one CSV file. | Multiple Failed Records in Same Email | 1.All failed records are listed. 2.No missing entries. 3.No duplicate entries. | Pass | Madhu Peketi | No | Cannot Automate
| NS | PRDOPS-490-TC-006 | Verify behavior when no failed sync records exist. | Negative Scenario – No Failed Records | No email sent (OR) Email sent indicating "No failed records" (as per business rule). | Pass | Madhu Peketi | No | Cannot Automate
PRDOPS-415 | SFDC/NS | PRDOPS-415-TC-001 | Verify that a new integration response record is created in NetSuite when SFDC Order does not capture NetSuite ID during booking. | Verify Integration Response Record Creation in NetSuite | 1.A new Integration Response Record is created in NetSuite. 2.Record contains error details indicating missing NetSuite ID in SFDC. 3.Timestamp and Order reference are correct. 4. Error Msg : Error Message: Could not find NetSuite_Order__c in SFDC ORDER. | Pass | Madhu Peketi | No | Cannot Automate
| SFDC/NS | PRDOPS-415-TC-002 | Verify that a new integration response record is created in NetSuite when SFDC Order does not capture NetSuite ID during booking. | Verify Integration Response Record Creation in NetSuite | 1.A new Integration Response Record is created in NetSuite. 2.Record contains error details indicating missing NetSuite ID in SFDC. 3.Timestamp and Order reference are correct. 4. Error Msg : Error Message: Could not find NetSuite_Order__c in SFDC ORDER | Pass | Madhu Peketi | No | Cannot Automate
| SFDC/NS | PRDOPS-415-TC-003 | Verify that Sync Status is updated to "Failed" in NetSuite Fulfillment Status Record.- Test Order EDI | Verify NS-SFDC Sync Status Updated to "Failed" | 1.NS-SFDC Sync Status = "Failed" 2.Failure reason logged properly. 3.No duplicate status updates. 4. Error Msg : Error Message: Could not find NetSuite_Order__c in SFDC ORDER | Pass | Madhu Peketi | No | Cannot Automate
| SFDC/NS | PRDOPS-415-TC-004 | Verify that Sync Status is updated to "Failed" in NetSuite Fulfillment Status Record.- Test Order Non-EDI - (Use Product :: SELECT Id, Name FROM Product2 WHERE Order_Fulfillment__c = 'Manual') | Verify NS-SFDC Sync Status Updated to "Failed" | 1.NS-SFDC Sync Status = "Failed" 2.Failure reason logged properly. 3.No duplicate status updates. 4. Error Msg : Error Message: Could not find NetSuite_Order__c in SFDC ORDER | Pass | Madhu Peketi | No | Cannot Automate
| SFDC/NS | PRDOPS-415-TC-005 | Verify that Sync Status is updated to "Failed" in NetSuite Fulfillment Status Record.- Test Order(Manual fulfilment) | Verify NS-SFDC Sync Status Updated to "Failed" | 1.NS-SFDC Sync Status = "Failed" 2.Failure reason logged properly. 3.No duplicate status updates. 4. Error Msg : Error Message: Could not find NetSuite_Order__c in SFDC ORDER | Pass | Madhu Peketi | No | Cannot Automate
| SFDC/NS | PRDOPS-415-TC-006 | Verify that Sync Status is updated to "Failed" in NetSuite Fulfillment Status Record.- Test for Renewal/ Amendment Order_Auto Fulfillment | Verify NS-SFDC Sync Status Updated to "Failed" | 1.NS-SFDC Sync Status = "Failed" 2.Failure reason logged properly. 3.No duplicate status updates. 4. Error Msg : Error Message: Could not find NetSuite_Order__c in SFDC ORDER | Pass | Madhu Peketi | No | Cannot Automate
| SFDC/NS | PRDOPS-415-TC-007 | Verify that Sync Status is updated to "Success" in NetSuite Fulfillment Status Record. | Verify NS-SFDC Sync Status Updated to "Success" | 1.NS-SFDC Sync Status = "Success" 2. Error Msg should not populate | Pass | Madhu Peketi | No | Cannot Automate
PRDOPS-413 | SFDC | PRDOPS-413-TC-001 | TC_Sync_001_QE_StandardSync | Verify that Opportunity and Opportunity Line updates successfully sync to Bookings, BLI, and Splits during the standard QE period. | The updated values from the Opportunity and Opportunity Lines are successfully and accurately synced to the corresponding Booking, BLI, and Booking Splits. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-002 | TC_Sync_002_QE_DebookingSync for Amount Based_Full | Verify that Debooking actions trigger correct updates to Bookings during the standard QE period. | The Debooking scenario is successfully processed, and the negative/adjustment values are accurately synced to the corresponding Booking, BLI, and Booking Splits. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-003 | TC_Sync_003_QE_DebookingSync for Line Item Based_Partial | Verify that Debooking actions trigger correct updates to Bookings during the standard QE period. | The Debooking scenario is successfully processed, and the negative/adjustment values are accurately synced to the corresponding Booking, BLI, and Booking Splits. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-004 | TC_Sync_004_QEPlus1_5PM_Sync | Verify that Opportunity updates successfully sync on QE+1 day at 5:00 PM PST/PDT. | The updates made at 5:00 PM PST/PDT are successfully synced to the corresponding Booking, BLI, and Booking Splits. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-005 | TC_Sync_005_QEPlus1_6PM_CornerCase_Sync | Verify the corner case where updates made exactly at the 6:00 PM PST/PDT cutoff on QE+1 sync within the following 15 minutes. | The changes are successfully synced to the corresponding Booking, BLI, and Booking Splits within a 15-minute window after the 6:00 PM save action. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-006 | TC_Sync_006_QEPlus1_Debooking_BeforeCutoff | Verify that Debooking actions successfully sync on QE+1 day prior to the 6:00 PM PST/PDT cutoff. | The Debooking action successfully syncs, and the adjustment Booking, BLI, and Splits are accurately reflected before the end of business hours. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-007 | TC_Sync_007_QEPlus1_8PM_FrozenSync | Verify that Booking sync is frozen and no updates occur for modifications made after the end of business hours (e.g., 8:00 PM PST/PDT) on QE+1. | The Booking sync is completely frozen. No updates occur to the Booking, Booking Splits, or BLI. The Booking retains its previous values. | Pass | Uma Mahesh | Yes | Partially Automated
| SFDC | PRDOPS-413-TC-008 | TC_Sync_008_QEPlus1_Debooking_Frozen | Verify that Debooking actions initiated after the end of business hours (e.g., 8:00 PM PST/PDT) on QE+1 do not sync to the frozen Bookings. | The Booking sync is frozen. The Debooking adjustments do not sync to or alter the frozen Booking, Booking Splits, or BLI. | Pass | Uma Mahesh | Yes | Partially Automated
PRDOPS-477 | SFDC/NS | PRDOPS-477_TC-01 | Verify If the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for Non-EDI. | Verify If the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for Non-EDI. | When the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-02 | Verify If the "Booked By" field is empty and the "Revised By" field is empty,then OM users (OM Manager) except the Revised user should be able to approve the order for Non-EDI. | Verify If the "Booked By" field is empty and the "Revised By" field is empty,then OM users (OM Manager) except the Revised user should be able to approve the order for Non-EDI. | When the "Booked By" field is empty and the "Revised By" field is empty,then OM users (OM Manager) except the Revised user should be able to approve the order for Non-EDI. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-03 | Verify if the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to Approve the Order in NS for Non-EDI. | Verify if the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to Approve the Order in NS for Non-EDI. | When the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to Approve the Order in NS. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-04 | Verify if the "Revised By" field is not empty and the assigned Reviser captured in the Revised by field then the Revised by user Can't be able to Approve the Order in NS for Non-EDI. | Verify if the "Revised By" field is not empty and the assigned Reviser captured in the Revised by field then the Revised by user Can't be able to Approve the Order in NS for Non-EDI. | When the "Revised By" field is not empty and the assigned Reviser captured in the Revised by field then the Revised by user Can't be able to Approve the Order in NS. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-05 | Verify if the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to uncheck the approval hold check box on the order | Verify if the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to uncheck the approval hold check box on the order | When the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to uncheck the approval hold check box on the order | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-06 | Verify if the "Booked By" field is not empty & Booker is not in the "Revised by" field then Booker Can't be able to Approve the Order & Can't be able to uncheck the Approval hold checkbox on the Order. | Verify if the "Booked By" field is not empty & Booker is not in the "Revised by" field then Booker Can't be able to Approve the Order & Can't be able to uncheck the Approval hold checkbox on the Order. | When the "Booked By" field is not empty & Booker is not in the "Revised by" field then Booker Can't be able to Approve the Order & Can't be able to uncheck the Approval hold checkbox on the Order. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-07 | Verify if the Second User updates the Order then "Submitter Email id" should be captured with the second person email id & Revised by should be captured his name. | Verify if the Second User updates the Order then "Submitter Email id" should be captured with the second person email id & Revised by should be captured his name. | When the Second person updates the Order then his name will capture in the Revised by. Now "Booker by" & "Revised by" both can't be able to approve the Order and Approval Hold button. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-08 | Verify if the Third User updates the Order then "Submitter Email id" should be captured with the second & Third person email id's & All Revised by should be captured his name. | Verify if the Third User updates the Order then "Submitter Email id" should be captured with the second & Third person email id's & All Revised by should be captured his name. | When the Third person updates the Order then his name will capture in the Revised by. Now "Booker by" & All "Revised by" can't be able to approve the Order and Approval Hold button. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-09 | Verify the Sync Timing issue by Updating the Same Order at the Sametime with different users. The Changes should sync from SFDC to NS. | Verify the Sync Timing issue by Updating the Same Order at the Sametime with different users. The Changes should sync from SFDC to NS. | When the User Sync the Same Order at the Sametime with different users then the Changes should sync from SFDC to NS. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-10 | Verify when the Order is cloned then then “Booked by” & “Revised by” field values should copy from Original Order to Cloned Order. | Verify when the Order is cloned then then “Booked by” & “Revised by” field values should copy from Original Order to Cloned Order. | When the Order is cloned then then “Booked by” & “Revised by” field values should copy from Original Order to Cloned Order. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-11 | Verify If the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for EDI. | Verify If the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for EDI. | When the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-12 | Verify if the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to Approve the Order in NS for EDI. | Verify if the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to Approve the Order in NS for EDI. | When the "Booked By" field is not empty and the assigned booker captured in the Booked by field then the Booker Can't be able to Approve the Order in NS. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-13 | Verify If the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for EDI. | Verify If the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for EDI. | When the "Booked By" field is empty and the "Revised By" field is not empty,then OM users (OM Manager) except the Revised user should be able to approve the order for EDI. | Pass | Sai Krishna | Yes | Partially Automated
| SFDC/NS | PRDOPS-477_TC-14 | Verify the Email verification if the Booked by user Email id is not present in NS. | Verify the Email verification if the Booked by user Email id is not present in NS. | The Email verification should be the Booked by user Email id is not present in NS. | Pass | Sai Krishna | Yes | Partially Automated
PRDOPS-470 | SFDC | PRDOPS-470_TC-01 | Verify the Success Report Should be created with “ROSM Stage 6 Automation Success Measurement” and verify the Calculation in the Report. | Verify the Success Report Should be created with “ROSM Stage 6 Automation Success Measurement” and verify the Calculation in the Report. | The Success Report Should be created with “ROSM Stage 6 Automation Success Measurement” and verify the Calculation in the Report. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-02 | Verify the Success Report Records & Success % when the New Renewal EDI Opportunity created and moved to Stage 6 through Automation. | Verify the Success Report Records & Success % when the New Renewal EDI Opportunity created and moved to Stage 6 through Automation. | The Success Report Records & Success % when the New Renewal EDI Opportunity created and moved to Stage 6 through Automation. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-03 | Verify the Success Report Records & Success % when the New Renewal PO PDF Opportunity created and moved to Stage 6 through Automation. | Verify the Success Report Records & Success % when the New Renewal PO PDF Opportunity created and moved to Stage 6 through Automation. | The Success Report Records & Success % when the New Renewal PO PDF Opportunity created and moved to Stage 6 through Automation. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-04 | Verify the Success Report Records & Success % when the New Renewal Non-EDI Opportunity created and moved to Stage 6 through Automation. | Verify the Success Report Records & Success % when the New Renewal Non-EDI Opportunity created and moved to Stage 6 through Automation. | The Success Report Records & Success % when the New Renewal Non-EDI Opportunity created and moved to Stage 6 through Automation. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-05 | Verify the Success Report Records & Success % when the New Renewal Non-EDI Opportunity created and moved to Stage 6 Manually. | Verify the Success Report Records & Success % when the New Renewal Non-EDI Opportunity created and moved to Stage 6 Manually. | The Success Report Records & Success % when the New Renewal Non-EDI Opportunity created and moved to Stage 6 Manually. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-06 | Verify the Success Report Records & Success % when the Quote update failed. (Quote is not Primary & not Approved). | Verify the Success Report Records & Success % when the Quote update failed. (Quote is not Primary & not Approved). | The Success Report Records & Success % when the Quote update failed. (Quote is not Primary & not Approved). | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-07 | Verify the Success Report Records & Success % & Failure report when the New Opportunity Failed to move to Stage 6 through Automation. | Verify the Success Report Records & Success % & Failure report when the New Opportunity Failed to move to Stage 6 through Automation. | The calculation should work as below formula Success % = ({Total Renewal Opportunities moved to Stage 6 by Automation}%{Total Renewal Opportunities NOT at Stage 6 when PO was received}) * 100 | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-08 | Verify the Filter conditions which are present in the Success Report | Verify the Filter conditions which are present in the Success Report | The Filter conditions which are present in the Success Report should work | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-09 | Verify the Failure Report which is updated with the “SS6 Automation Failure for Renewal Opp”. | Verify the Failure Report which is updated with the “SS6 Automation Failure for Renewal Opp”. | The Failure Report should be updated with the “SS6 Automation Failure for Renewal Opp”. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-470_TC-10 | Verify the Filter Conditions for the Failure Report | Verify the Filter Conditions for the Failure Report | The Filter conditions which are present in the Failure Report should work | Pass | Sai Krishna | Yes | Yet To Automate
PRDOPS-23 | SFDC | PRDOPS-23_TC-01 | Verify the Auto Order Submission for Sub-type = "GC OnDemand" and when the Order is created then it should submit automtically without any hold | Verify the Auto Order Submission for Sub-type = "GC OnDemand" and when the Order is created then it should submit automtically without any hold | When the Order is Auto Submission for Sub-type = "GC OnDemand" and when the Order is created then it should submit automtically without any hold | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-23_TC-02 | Verify the GC OnDemand Order is Auto Submitted & Order is Shipped then Overage Orders should create automatically. | Verify the GC OnDemand Order is Auto Submitted & Order is Shipped then Overage Orders should create automatically. | When the GC OnDemand Order is Auto Submitted & Order is Shipped then Overage Orders should create automatically. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-23_TC-03 | Verify the Manual Order Submission for Sub-type = "GC OnDemand" & Subscription Term on the Order Product is blank and the Subscription Pricing is populated and When the OM user clicks on ‘Submit Order’ button then the validation “Subscription Term must be stamped on Order Product in order to submit Order” is bypassed and the order is submitted successfully. | Verify the Manual Order Submission for Sub-type = "GC OnDemand" & Subscription Term on the Order Product is blank and the Subscription Pricing is populated and When the OM user clicks on ‘Submit Order’ button then the validation “Subscription Term must be stamped on Order Product in order to submit Order” is bypassed and the order is submitted successfully. | When the Manual Order Submission for Sub-type = "GC OnDemand" & Subscription Term on the Order Product is blank and the Subscription Pricing is populated and When the OM user clicks on ‘Submit Order’ button then the validation “Subscription Term must be stamped on Order Product in order to submit Order” is bypassed and the order is submitted successfully. | Pass | Sai Krishna | Yes | Yet To Automate
| SFDC | PRDOPS-23_TC-04 | Verify the Order Submission when Type = GC OnDemand and Order went On Hold as the maximum commit value were blank on the overage orders and when the OM user go to the “Overage Orders with Maximum Commit values are Blank” report then the Overage order should appear in the report. | Verify the Order Submission when Type = GC OnDemand and Order went On Hold as the maximum commit value were blank on the overage orders and when the OM user go to the “Overage Orders with Maximum Commit values are Blank” report then the Overage order should appear in the report. | When the Order Submission when Type = GC OnDemand and Order went On Hold as the maximum commit value were blank on the overage orders and when the OM user go to the “Overage Orders with Maximum Commit values are Blank” report then the Overage order should appear in the report. | Pass | Sai Krishna | Yes | Yet To Automate

## Sheet1
QA Summary of Story Cards:
Track | QA Qualified | QA Completed | Ready for UAT | UAT Completed | Savings due to Test Automaton in hrs / Sprint
PRDOPS | 6 | 6 | 5 | 1 | 14 hr
QA Summary of Test Cases:
Sl No | Story Cards | Total no. of Test Cases | Pass | Execution % | Defects | Defect Density (%) | Defect Leakage (%) | Defect Rejection Rate (%) | QA Automation Savings in (hrs) | Comments |  | Defects | P0 | P1 | P2 | P3 | No Action
1 | PRDOPS-490 | 6 | 6 | 100% | 1 | 16.6667 | 0 | 0 | 2 | We have used our test automation for test data creation. |  | 1 | 0 | 0 | 1 | 0 | 0
2 | PRDOPS-415 | 7 | 7 | 100% | 1 | 14.2857 | 0 | 0 | 2 |  |  | 1 | 0 | 0 | 1 | 0 | 0
3 | PRDOPS-477 | 14 | 14 | 100% | 3 | 21.4286 | 0 | 0 | 2 |  |  | 3 | 1 | 2 | 0 | 0
4 | PRDOPS-470 | 10 | 10 | 100% | 1 | 10 | 0 | 0 | 4 |  |  | 1 | 0 | 0 | 1 | 0 | 1
5 | PRDOPS-413 | 8 | 8 | 100% | 0 | 0 | 0 | 0 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | PRDOPS-23 | 4 | 4 | 100% | 1 | 25 | 0 | 0 | 0 | Scripting is in progress for On Demand orders. |  | 1 | 1 | 0 | 0 | 0 | 2
6 | 0 | 49 | 49 | 100% | 7 | 14.5635 | 0 | 0 | 14 |  | Total | 7 | 2 | 2 | 3 | 0 | 3
[11 empty] | Other Issues/No Action | 3
Bug Report : | [10 empty] | Total Issue | 10
While testing the above test execution we have come across the following defects in QA Sandbox.
Total Number of Defects |  | Close | Defect Leakage to UAT | Defect Leakage to UAT (%)
P0 | 2 | 2 | 0 | 0%
P1 | 2 | 2 | 0
P2 | 3 | 3 | 0